## Slide 1: Effective Turnaround/Shutdown Planning
Turnaround (T/A) maintenance is defined as the maintenance carried out on a plant in a period of time when loss of production has been accommodated in the current production schedule for the purpose of significant mechanical repair;
It includes preparatory and execution work even if they fall outside the period when the plant is shutdown;

## Slide 2: Phases of Turnaround
The completion of one Turnaround is the starting point of the next cycle. During this period the following activities take place:
Unit performance evaluation by comparing present and anticipated performance;
Capital expenditure and improvement plans;
Regulatory and legal requirements.
Important Milestones
-18 Months
-12 Months
-6 Months
Start Date
+1 Month
After Finish Date
Finish Date

## Slide 3: Phases of Turnaround
PHASE 1: Preliminary development
All activities related to the preliminary development should be completed 18 months prior to the commencement date of the T/A
Appointment of Turnaround Manager;
Formation of Steering Committee;
Establish turnaround philosophy;
Identify sources of work orders (CMMS, Inspection schedule);
Review lessons learned, best practices;
Preliminary Budget (± 30%).

## Slide 4: Phases of Turnaround
PHASE 2: Work development
This phase commences 18 months before the shutdown and should be completed 12 months prior to the shutdown commencement.
Job list collection (Capital or Improvement projects, safety and environmental items, inspection requests, operational and technological requests e.g. catalysts unloading);
Contractor Pre-qualification;
Establishment of document control system;
Identification of long delivery materials;
Budget (± 20%).

## Slide 5: Phases of Turnaround
PHASE 3: Detailed planning/Pre-Turnaround work
This phase commences 6 months prior to the shutdown and should be completed just before the commencement date.
Contract tendering;
Capital projects engineering phase completion;
Detailed safety and security plan;
Additional work control procedure;
Special tools/services requirements (scaffolding, NDT, etc.);
Facilities planning;
Mobilization of selected contractors;

## Slide 6: Phases of Turnaround
Finalization of schedule and recourse optimization;
Materials on site;
Temporary facilities preparation;
Special tools and equipment on site;
Job and spade location tagging;
Pre-fabrication work;
Scaffolding erection;
Work permit preparation;
Operational fittings, hoses and blinds.

## Slide 7: Phases of Turnaround
PHASE 4: Turnaround execution
The execution phase is the most critical phase of the turnaround.
Safety, quality and environmental management systems;
Unit shutdown, steaming out and equipment release for entry;
Daily management meetings;
Daily progress report;
Daily additional work & scope growth review (Inspection action reports) ;
Pre-commissioning and unit start-ups.

## Slide 8: Phases of Turnaround
PHASE 5: Post-Turnaround work
During this stage the following activities take place:
Demobilization of contractors;
Removal of temporary facilities;
Materials returned to warehouse;
Final report and lessons learned review;
Repair and inspection history report;
Final cost analysis;
Recommendation for next turnaround.